## POA-v1
CUSTOMER NAME : Precision Group |  |  |  | Doc No | PI-RIM-DN-001
PROJECT NAME : DayNight Terraform Infrastructure Deployment (UAT & PROD) |  |  |  | Doc Version | Ver 1.0
PRODUCTS : AWS Cloud Infrastructure (UAT & PROD) |  |  |  | Project Engineer | Ashim M
PROJECT START DATE : 13-February-2026 |  |  |  | Project Location | Chennai
PROJECT END DATE : 16-February-2026 |  |  |  | Customer SPOC | To be filled
S.No | Activity | Description | Owner | Approx. Timeline | Support Mode | Start Date | End Date | Dependency | Remarks
Phase 1: | Requirement Validation & Planning |  |  | 6 Hours |  | 2026-02-13 | 2026-02-13
1.1 | Requirement Discussion | Confirm architecture, GitHub repo, AWS region, tagging standards | Precision | 2 Hours | Remote |  |  | IAM Access | Completed
1.2 | Access Verification | Validate AWS IAM permissions & CodeConnections |  | 2 Hours
1.3 | Architecture Finalization | Review UAT → PROD workflow & approval mechanism |  | 2 Hours
Phase 2: | UAT Infrastructure Deployment |  |  | 14 Hours |  | 2026-02-13 | 2026-02-14
2.1 | Terraform Initialization | Setup Terraform modules & variables for UAT | Precision | 3 Hours | Remote |  |  | Terraform Init SNS Created SNS Confirmed UAT Infra Ready | Completed
2.2 | Deploy UAT Core Infra | Create S3, CloudFront, Lambda, SNS |  | 5 Hours
2.3 | SNS Subscription Confirmation | Confirm email subscription for notifications |  | 1 Hour
2.4 | UAT Pipeline Setup (Disabled) | Configure CodePipeline with enable_pipeline = false |  | 3 Hours
2.5 | UAT Functional Validation | Validate static hosting & CloudFront access |  | 2 Hours
Phase 3: | Production Infrastructure Deployment |  |  | 12 Hours |  | 2026-02-14 | 2026-02-15
3.1 | Terraform Initialization (Prod) | Configure PROD variables & remote state reference | Precision | 3 Hours | Remote |  |  | UAT Completed | Completed
3.2 | Deploy PROD Core Infra | Create S3, CloudFront, Lambda, Pipeline |  | 5 Hours
3.3 | PROD Validation | Validate static hosting & pipeline execution |  | 2 Hours
3.4 | Initial PROD Deployment Test | Trigger first deployment & verify execution |  | 2 Hours
Phase 4: | UAT Pipeline Enablement & Promotion Workflow |  |  | 8 Hours |  | 2026-02-15 | 2026-02-16
4.1 | Enable UAT Pipeline | Update enable_pipeline = true & apply | Precision | 2 Hours | Remote |  |  | PROD Ready | Completed
4.2 | UAT Deployment Test | Validate success notification email |  | 2 Hours
4.3 | Approval Workflow Testing | Validate approval email triggers PROD |  | 2 Hours
4.4 | End-to-End Validation | Full UAT → Approval → PROD workflow test |  | 2 Hours
Phase 5: | Security, Documentation & KT |  |  | 8 Hours |  | 2026-02-16 | 2026-02-16
5.1 | Security Review | Validate IAM roles, OAC, S3 policies | Precision | 2 Hours | Remote |  |  | KT Completed | Pending
5.2 | Documentation Preparation | README, Setup Guide, Troubleshooting |  | 3 Hours
5.3 | Knowledge Transfer Session | Explain Terraform structure & pipeline flow |  | 2 Hours
5.4 | Final Sign-Off | Customer validation & approval |  | 1 Hour
RollBack
R1 | UAT Rollback | Revert to previous stable Terraform state | Precision | 1 Hour | Remote | N/A |  | Terraform State Available | Completed
R2 | PROD Rollback | Reapply previous Terraform state |  | 1 Hour |  |  |  | UAT Stable
R3 | Manual Intervention | Disable pipeline if unexpected issue |  | 30 Minutes
R4 | Restore Infrastructure | Redeploy infrastructure using Terraform |  | 2 Hours |  |  |  | Backup State